## OPMS
Doc 1
ANNUAL PERFORMANCE REPORT
IDP / SDBIP NO. | NATIONAL KEY PERFORMANCE AREAS | OBJECTIVE (AS PER IDP) | STRATEGIES (AS PER IDP) | INDICATORS | Annual |  | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4 |  | Status (Achieved / Not Achieved) |  | Measures taken to improve performance | Portfolio of Evidence
[5 empty] | ANNUAL TARGET) | ANNUAL ACTUAL | Target | Actual | Reasons for under performance | Target | Actual | Reasons for under performance | Target | Actual | Reasons for under performance | Target | Actual |  | Reasons for under performance
1.1.1 | BASIC SERVICE DELIVERY | To provide a better local access road network | To increase the number of roads built per year | The number of kilometres of access roads completed | Completion of Project (previously rolled over projects) :Sobho road 5.5km and Nokopela road 7km by 30 December 2015 | Sobho Road 5.5 Km Completed on 09 November 2015. Nokopela Road 7.8km completed on 15 September 2015. | Completion of 5.5 km of Sobho road and 7.8 km of Nokopela road by 30 September 2015 | Construction of 5.5 km of Sobho road not met. Construction of 7.8 km of Nokopela road completed on 15 September 2015 | Poor performance by the service provider | Projects completion and hand-over by 3 December 2015 | Construction of 5.5 km of Sobho road completed on 02 December 2015 but defects were noted by the inspector, therefore, target not met. | Inspectors noted defects in the Sobho road. Constractor to return back on site to rectify faults declared | Constractor to finalize faults detected by the inspectors on 02 December 2015 | Project complete, inspectors declared the road as satisfactory on 19 January 2016 | n/a |  |  | Achieved | n/a | n/a | Certificate of completion
1.1.2 |  |  |  |  | Construction of 11.5 kilometres of access road at Emswaneni by 30 June 2016. | Target not met. Emswaneni road 9.7 km completed by 30 June 2016. | Completion of project designs by 30 September 2015 | Projects designs completed by 30 September 2015 | n/a | Appointment of the contractor by 30 December 2015 | Procurement completed and contractor appointed on 03 November 2015 | n/a | Site establishment, clearing and grubbing and earthworks by 30 March 2016 | Site establishment, clearing and grubbing and earthworks completed on 31 March 2016 | n/a | Completion and project hand over by 30 June 2016 | Emswaneni road 9.7 km completed by 30 June 2016 (target not met) | Not Achived | The decline in number of kilometres constructed resulted from the fact that the municipality has a 3 year plan, when the project is identified to be done in three years' time, most of the councillors do not consult thoroughly with the community. This has resulted in a decrease or change in the scope of works during project design stage when kilometres are actually measured. | The municipality will hire a facilitator to conduct thorough consultations with the community to obtain accurate number of kilometres to be constructed | Certificate of completion
1.1.3 |  |  |  |  | Construction of 7 kilometres of access road at Guswini by 30 June 2016. | Target not met. Guswini road 6.7 km completed on 16 October 2015 . | Site establishment, clearing and grubbing and earthworks by 30 September 2015 | Site establishment, clearing and grubbing and earthworks completed by 30 September 2015 | n/a | Project completion by 30 December 2015 | 6.7 kilometres of access road completed at Guswini on 16 October 2015 | n/a | [5 empty] | Not achieved |  |  | Completion certificate
1.1.4 |  |  |  |  | Construction of 7 kilometres of access road at Ndanyana by 30 June 2016. | Target not met. 6.9km of access road at Ndanyana completed on 16 August 2016. | Completion of project designs by 30 September 2015 | Projects designs completed by 30 September 2015 | n/a | Appointment of the contractor by 30 December 2015 | Procurement completed and contractor appointed on 09 October 2015 | n/a | Site establishment, clearing and grubbing and earthworks by 30 March 2016 | Site establishment, clearing and grubbing completed on 17 March 2016. earthworks incomplete | Poor weather conditions | Completion and project hand over by 30 June 2016 | Construction of 6.9km at Ndanyana completed on 16 August 2016 | Not achieved |  |  | Completion certificate
1.1.5 |  |  |  |  | Construction of 7 kilometres of access road at Mbhono by 30 June 2016. | Target not met. 7km of access road at Mbhono completed on 17 July 2016. | Completion of project designs by 30 September 2015 | Projects designs completed by 30 September 2015 | n/a | Appointment of the contractor by 30 December 2015 | Procurement completed and contractor appointed on 03 November 2015 | n/a | Site establishment, clearing and grubbing and earthworks by 30 March 2016 | Site establishment, clearing and grubbing completed on 17 March 2016. earthworks incomplete | Poor weather conditions | Completion and project hand over by 30 June 2016 | 7km at Umbhono road completed on 18 July 2016 | Not achieved |  |  | Completion certificate
1.1.6 |  |  |  |  | Construction of 7 kilometres of access road at Ngubukazi by 30 June 2016. | Construction of 6.6 kilometres of access road at Ngubukazi completed on 09 November 2015. | Completion of project designs by 30 September 2015 | Projects designs completed by 30 September 2015 | n/a | Construction complete and project hand-over | Construction of 6.6 kilometres of access road at Ngubukazi completed on 09 November 2015. | This project was merged with Sobho road. | [5 empty] | Achieved | n/a | n/a | Certificate of completion (Sobho)
1.1.7 |  |  |  |  | Construction of 6.4 kilometres of access road at Mahlashana by 30 November 2016. | Construction of 6.4 kilometres of access road at Mahlashana is in progress to be completed by 30 November 2016. | [9 empty] | Appointment of a constructor by 30 June 2016 | Constructor appointed on 16 April 2016 | Achieved | The project was scheduled to commence in May 2016 and completed on 30 Novemeber 2016 due to budget constraints. | Rolled over to 2016/2017 | Appointment letter
1.1.8 |  |  |  |  | Construction of 2.4 kilometres of access road at Pomeroy internal roads by 30 September 2015. | Target not met. | Completing 70% construction of the project | 51% of the project was completed on 30 September 2015 | Lack of performance by the service provider | Project completion by 30 December 2015 | No progress (No information was provided as an evidence) | Lack of performance by the service provider | Project completion by 30 March | No progress (No information was provided as an evidence) | Lack of performance by the service provider | Project completion by 30 June 2016 | Target not met | Not Achieved | Lack of performance by the service provider. | Municipality is implimenting penality clauses | n/a
1.2.1 |  |  | to ensure proper maintanace of access roads | Number of maintained access roads | Maintenance of 3.5km of gravel roads at Nkonyane by 30th June 2016. | Maintenance of 3.5 kilometres of access road at Nkonyane completed on 18 December 2015. |  |  |  | Maintenance of 3.5 kilometres of access road at Nkonyane by 30 December 2015 | Maintenance of 3.5 kilometres of access road at Nkonyane completed on 18 December 2015 | n/a | [5 empty] | Achieved | n/a | n/a | Certificate of completion
1.2.2 |  |  |  |  | Maintenance of 4.9km of gravel roads at Tailor by 30th June 2016. | Maintenance of 4.9 kilometres of access road at Tailor completed by 30 January 2016. |  |  |  | Appointment of service provider and maintenance of 4.9km of gravel roads at Tailor by 30th December 2015 | Service provider appointed on 09 October 2015 | n/a | Completion of the maintenance of 4.9km of gravel roads at Tailor by 30th March 2015 | Maintenance of 4.9 kilometres of access road at Tailor completed by 30 January 2016. | n/a |  |  | Achieved | n/a | n/a | Certificate of completion
1.2.3 |  |  |  |  | Maintenance of Mzweni concrete slab by 30th December 2015. | Maintenance of Mzweni concrete slab completed on 10 December 2015. |  |  |  | Appointment of service provider and maintenance of Mzweni concrete slab by 30th December 2015 | Service provider appointed on 13 October 2015 and maintenance completed on 10 December 2015 | n/a | [5 empty] | Achieved | n/a | n/a | Completion certificates
1.3.1 |  | To reduce sporting facilities backlog within the municipal area | Upgrading of sport facilities | Number of sport facilities upgraded | Upgrading Umzisho sport field by 30 June 2016. | Target not met | Online submission of business plan to MIG by 30 September 2015 | Business Plan is on MIG system ,was submited but not approved as yet. | n/a | Obtain funds from MIG to commence project design by 30 December 2015 | Target not met | Could not secure funding from MIG | Obtain funds from MIG to commence project design by 30 December 2015 | Target not met | Could not secure funding from MIG | Obtain funds from MIG to commence project design by 30 December 2015 | Target not met | Not Achived | We could not secure funding from MIG. | A follow up will be conducted on the business plans we submitted to funders. | n/a
1.3.3 |  |  | Maintenance of sport fields | Number of sport fields maintained | Maintenance of 8 sports fields with 1 sport field in Pomeroy, Fabeni, Shiyane , Ezindluzeleni, Nyoniyezwe, Mzisho, Ehlanzeni and Gxobanyawo by 30 June 2016. | Maintenance of 4 sports fields with 1 sport field in Pomeroy, Ezindluzeleni, Mzisho and Gxobanyawo completed by 30 June 2016. | 3 (monthly reports per quarter per sport field) | On going service- Pomeroy -( reports Submitted) Ezindluzeleni ( reports Submitted) Mzisho ( reports Submitted) | Enhlanzeni/Ntanyana sport field-sport field needs to be renovated -Efabeni - caretaker was not hired and there is no formal reporting .Shiyane -did not have caretaker. Gxobanyawo previous caretaker passed away . | 3 (monthly reports per quarter for each sport field) | On going service- Pomeroy -( reports Submitted) Ezindluzeleni ( reports Submitted) Mzisho ( reports Submitted) | Enhlanzeni/Ntanyana sport field-sport field needs to be renovated -Efabeni - caretaker was not hired and there is no formal reporting .Shiyane -did not have caretaker Gxobanyawo previous caretaker passed away . | 3 (monthly reports per quarter for each sport field) | On going service- Pomeroy -( reports Submitted) Ezindluzeleni ( reports Submitted) Mzisho ( reports Submitted) | Enhlanzeni/Ntanyana sport field-sport field needs to be renovated -Efabeni - caretaker was not hired and there is no formal reporting .Shiyane -did not have caretaker Gxobanyawo previous caretaker passed away . | 3 (monthly reports per quarter for each sport field) | On going service- Pomeroy -( reports Submitted) Ezindluzeleni ( reports Submitted) Mzisho ( reports Submitted) | Not Achieved | Nyoniyezwa doesn’t have a caretaker because the stadium is not functional, its renovations was not budgeted for in the 2015/16 financial year. Shiyane doesn’t have a caretaker due to budget constraints. Fabeni uses waste general workers to do the maintenance because there is no budget for a caretaker. | Nyonezwe stadium will be renovated in the 2017/2018 financial year. Fabeni will continue being maintained by the waste general workers amd they will be instructed to prepare quarterly reports . A caretaker to oversee Shiyane was recruited on 10 June 2016. | Quarterly reports
1.4.1 |  | To accelerate electrification of Msinga | To provide an acceptable standard of electricity | Number of houses provided with access to electricity | Electrification of 2420 households at Douglas (310), Mzweni phase I (500), Ekuvukeni (610) and Mabaso (1000) households by 30th June 2016. | Target not met. Completion is as follows: Douglas 75%, Mzweni 94%, Ekuvukeni 98% and Mabaso 79%. | Appointment of the consultants and contractors by 30 September 2015 | Appointment of the consultants and contractors for Mabaso, Ekuvukeni, Mzweni, Mashunka and a consultant for Douglas was conducted by 30 September 2015 | n/a | Appointment of Douglas contractor, digging of holes and planting of structures by 30 December 2015 | Douglas contractor appointed on 03 November 2015, digging of holes and planting of structures by 30 December 2015 | n/a | Stringing of wires and installation of meter box by 30 December 2015 | Stringing of wires and installation of meter box completed by 30 December 2015 | n/a | Project completion and commissioning by 30 June 2016 | Target not met. Completion is as follows: Douglas 75%, Mzweni 94%, Ekuvukeni 98% and Mabaso 79%. | Not achieved | Delays are due to poor weather conditions and rocks challenges. Mzweni and Ekuvukeni were completed in the month of July 2016. | 2016/2017 financial year projects completion dates to have an extension period to accommodate possible delays or challenges. | Progress reports
1.4.2 |  |  |  |  | Appointment of service provider for electrification of 1284 households at: Nogawu (162) Nhlesi/Ngcuba (171) Mahlabathini (79) Mbhono (172) Othame (190) Dwayiswayo(180) Simanyana(171) Ezingulubeni (159) by 30 April 2016 | Service provider electrification of 1284 households appointed on 16 April 2016 | [9 empty] | Appointment of a consultant by 30 June 2016 | Service provider for electrification of 1284 households appointed on 16 April 2015 | Achieved | n/a | n/a | Appointment letter
1.5.1 |  | To ensure proper waste management | To properly process waste in an environmentally safe and sustainable way | Number of days of refuse collection. | Refuse to be collected 6 times a week for 52 weeks at Pomeroy, Tugela Ferry and Keats Drift by 30 June 2016. | Refuse collected 6 times a week for 52 weeks at Pomeroy, Tugela Ferry and Keats Drift. | Refuse to be collected 6 times a week for 52 weeks at Pomeroy, Tugela Ferry and Keats Drift by 30 September 2015 | Refuse collected 6 times a week for 52 weeks at Pomeroy, Tugela Ferry and Keats Drift. | n/a | Refuse to be collected 6 times a week for 52 weeks at Pomeroy, Tugela Ferry and Keats Drift by 30 December 2015 | Refuse collected 6 times a week for 52 weeks at Pomeroy, Tugela Ferry and Keats Drift. | n/a | Refuse to be collected 6 times a week for 52 weeks at Pomeroy, Tugela Ferry and Keats Drift by 30 March 2016. | Refuse collected 6 times a week for 52 weeks at Pomeroy, Tugela Ferry and Keats Drift. | n/a | Refuse to be collected 6 times a week for 52 weeks at Pomeroy, Tugela Ferry and Keats Drift by 30 June 2016. | Refuse collected 6 times a week for 52 weeks at Pomeroy, Tugela Ferry and Keats Drift. | n/a | n/a | n/a | Minutes
1.5.2 |  |  | Installation of bins and skips | Number of bins and skips installed. | Installation of 100 skips and 2000 bins at Tugela Ferry, Keats Drift and Pomoroy by 30 June 2016. | Target not met. Budget constraints, could not secure funding. | [11 empty] | Not achieved | Budget constraints. Could not secure funding. | To secure funding in 2016/2017 financial year. | N/A
1.6.1 |  | To provide safe and sustainable living environment | To facilitate the development of rural housing | The number of housing projects facilitated. | 6 housing projects facilitation meetings to be held by 30 June 2016 for Ezibomvini, KwaMthembu, Mvundlwini, Pomeroy, Latha and Kwadolo. | Only 1 housing forum meeting sat on 12 February 2016 | 2 housing projects facilitation meetings to be held by 30 September 2015 for Ezibomvini, KwaMthembu, Mvundlwini, Pomeroy, Latha and Kwadolo. | Target not met | Representatives from the Human Settlements were requested to attend scheduled meetings but no attendance was noted | 2 housing projects facilitation meetings to be held by 30 December 2015 for Ezibomvini, KwaMthembu, Mvundlwini, Pomeroy, Latha and Kwadolo. | Target not met | Representatives from the Human Settlements were requested to attend scheduled meetings but no attendance was noted | 1 housing projects facilitation meetings to be held by 30 March 2016 for Ezibomvini, KwaMthembu, Mvundlwini, Pomeroy, Latha and Kwadolo. | 1 housing forum meeting sat on 12 February 2016 | Representatives from the Human Settlements were requested to attend scheduled meetings but no attendance was noted | 1 housing projects facilitation meetings to be held by 30 June 2016 for Ezibomvini, KwaMthembu, Mvundlwini, Pomeroy, Latha and Kwadolo. | Target not met | Not achieved | Representatives from the Human Settlements were requested to attend scheduled meetings but no attendance was noted | Communication will be sent to the Human Settlement's offices to request a meeting and an emphasis will be made on the importance of the forum meetings | N/A
1.7.1 |  | To ensure proper construction of community facilities | Construction of community halls | Number of completed community halls. | Construction of 34 community halls by 30 June 2016. KoNdlovu, Emvondweni, Gunjwana, Esijozi, Esifuleni, Mzisho, Ngabayeni, Mkhovini, Dayiswayo, Ntanyana, Emfihlane, Mkhuphula, Mjintini, Ngcengeni, Mseleni, Nzala, Mbono, Ndaya, Msizini, Gabela, Mkhuphulangwenya, Esiphongweni, Ezindulini, Dolo, Mkhuphula, Ndaya, Simakadeni and Enhlanhleni, Esinyameni, Ekuvukeni, Gqohi, Mthaleni, Hohoza, Mambeni and Ntokozweni community halls was completed by 30 June 2016 | Construction of Esinyameni, Ekuvukeni, Gqohi, Mthaleni, Hohoza, Mambeni, Emvondweni, Gunjwana, Esijozi, Esifuleni, Mzisho, Ngabayeni, Mkhovini, Dayiswayo, Ntanyana, Emfihlane, Mkhuphula, Mjintini, Ngcengeni, Mseleni, Mbono, Gabela, Mkhuphulangwenya, Ntokozweni, Esiphongweni, Simakadeni and Enhlanhleni sport fields by 30 January 2016 | Appointment of 34 contractors by 30 September 2015 | 34 Contractors were appointed by 30 Septermber 2015 | n/a | Construction at 60% by 30 December 2015 | No progress reports /Supporting evidence that were prepared during the construction of communtiy halls | There are no reasons since there are no progress reports, variance cannot be detected | Construction at 80% by 30 March 2016 | No progress reports /Supporting evidence that were prepared during the construction of communtiy halls | There are no reasons since there are no progress reports, variance cannot be detected | Project completion by 30 June 2016 | Construction of KoNdlovu, Emvondweni, Gunjwana, Esijozi, Esifuleni, Mzisho, Ngabayenga, Mkhovini, Dayiswayo, Ntanyana, Emfihlane, Mkhuphula, Mjintini, Ngcengeni, Mseleni, Nzala, Mbono, Ndaya, Msizini, Gabela, Mkhuphulangwenya, Esiphongweni, Ezindulini, Dolo, Mkhuphula, Ndaya, Simakadeni and Enhlanhleni community halls was completed by 30 June 2016 but no supporting documentation was provided to validate the achievement. | Not achieved | Construction of KoNdlovu, Nzala, Msizini, Ezindulini, Dolo, Mkhuphula, Ndaya, and community halls was completed by 30 June 2016 but no supporting documentation was provided to validate the achievement. | Supporting documentation for construction of community halls (Certificates of completion) will be filed and kept for audit trail | Certificates of completion
2.1.1 | MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | To develop staff skills in the workplace in line with the IDP functions | To implement the workplace skills plan | The number of staff attending trainings. | 10 staff members to attend MFMP training. 20 staff members to enroll for administration in local government. 1 staff member to attend advanced MFMP course. 1 employee on project management. 1 on archives & record keeping course by 30th June 2016. | Target not met | Training of 10 staff members on MFMP by 30 September 2015 | Target not met | Training of staff members conducted but no supporting documentation was provided to validate the achievement. | 20 staff members to enroll for administration in local government by 30 December 2015 | Target not met | Training of staff members conducted but no supporting documentation was provided to validate the achievement. | Training of 1 staff member on advanced MFMP course and 1 on 1 employee on project management by 30 March 2016 | Target not met | Training of staff members conducted but no supporting documentation was provided to validate the achievement. | Training of 1 on archives & record keeping course by 30th June 2016. | Target not met | Training of staff members conducted but no supporting documentation was provided to validate the achievement. | Training of staff members conducted by 30 June 2016 but no supporting documentation was provided to validate the achievement. | Supporting documentation for training of staff members (Competency certificates) will be filed and kept for audit trail | Certificates
2.2.1 |  | Effective maintenance of municipal facilities | To ensure effective functioning of municipal facilities | Number of functional municipal facilities. | To maintain the Municipal Library throughout the financial year. | Library maintained functionally throughout the financial year. | To maintain the Municipal Library throughout the financial year. | Library maintained functionally throughout the financial year. | n/a | To maintain the Municipal Library throughout the financial year. | Library maintained functionally throughout the financial year. | n/a | To maintain the Municipal Library throughout the financial year. | Library maintained functionally throughout the financial year. | n/a | To maintain the Municipal Library throughout the financial year. | Library maintained functionally throughout the financial year. | n/a | n/a | n/a | Expenditure reports
2.2.2 |  |  |  |  | To mantain the municipal thusong centres functionally throughout the financial year. | Target not met | To mantain the municipal thusong centres functionally throughout the financial year. | Target not met | Maintenance of Thusong Centres conducted but no supporting documentation was provided to validate the achievement. | To mantain the municipal thusong centres functionally throughout the financial year. | Target not met | Maintenance of Thusong Centres conducted but no supporting documentation was provided to validate the achievement. | To mantain the municipal thusong centres functionally throughout the financial year. | Target not met | Maintenance of Thusong Centres conducted but no supporting documentation was provided to validate the achievement. | To mantain the municipal thusong centres functionally throughout the financial year. | Target not met | Maintenance of Thusong Centres conducted but no supporting documentation was provided to validate the achievement. | Maintenance of Thusong Centres performed throghout the financial year but no supporting documentation was provided to validate the achievement. | Supporting documentation for maintenance of Thusong Centres (expenditure reports) will be filed and kept for audit trail | n/a
2.2.3 |  |  |  |  | To mantain the municipal curio shop functionally throughout the financial year. | Target not met | To mantain the municipal curio shop functionally throughout the financial year. | Target not met | Maintenance of curio shop conducted but no supporting documentation was provided to validate the achievement. | To mantain the municipal curio shop functionally throughout the financial year. | Target not met | Maintenance of curio shop conducted but no supporting documentation was provided to validate the achievement. | To mantain the municipal curio shop functionally throughout the financial year. | Target not met | Maintenance of curio shop conducted but no supporting documentation was provided to validate the achievement. | To mantain the municipal curio shop functionally throughout the financial year. | Target not met | Maintenance of curio shop conducted but no supporting documentation was provided to validate the achievement. | Maintenance of curio shop performed throghout the financial year but no supporting documentation was provided to validate the achievement. | Supporting documentation for maintenance of curio shop (expenditure reports) will be filed and kept for audit trail | n/a
3.1.1 | LOCAL ECONOMIC DEVELOPMENT | To reduce poverty through LED | To implement the LED strategy | Implemented LED strategy. | Implementation of 2 LED projects identified in the LED strategy by 30 June 2016. | Target not met | [6 empty] | Implementation of 2 LED projects identified in the LED strategy by 30 June 2016. | Target not met | 2 LED projects were implemented by 30 June 2016. i.e One village One Product (OVOP) and Agri-processing plant but no supporting documentation was provided to validate the achievement. | Implementation of 2 LED projects identified in the LED strategy by 30 June 2016. | Target not met | Not achieved | 2 LED projects were implemented by 30 June 2016. i.e One village One Product (OVOP) and Agri-processing plant but no supporting documentation was provided to validate the achievement. | Supporting documentation for implementation of the LED projects ( reports) will be filed and kept for audit trail | n/a
3.1.2 |  |  | To increase the agricultural production through encouraging the community | Agricultural materials provided. | To allocate funding of R67 474.00 to each ward in the Msinga area for agricultural projects/activities by 30 June 2016 | Agricultural projects funded, each ward was given R67 474.00 to spend as per ward plan. | To fund agricultural projects for 4 wards by 30 September 2015 | 4 wards were funded by 30 September 2015 | n/a | To fund agricultural projects for 4 wards by 30 September 2015 | 4 wards were funded by 30 September 2015 | n/a | To fund agricultural projects for 4 wards by 30 September 2015 | 4 wards were funded by 30 September 2015 | n/a | To fund agricultural projects for 4 wards by 30 September 2015 | 4 wards were funded by 30 September 2015 | n/a | n/a | n/a | Control file
3.1.3 |  |  | operationailsation of the agricultural processing plant | Number of jobs created. | Spending the amount funded by COGTA to increase job employment | Target not met | [9 empty] | Spending the amount funded by COGTA to increase job employment | Target not met | Not achieved | The municipality could not secure funding from COGTA | n/a | n/a
3.1.4 |  |  | To nature the unique talent of Msinga | Number of acts that perfom at Mayoral izimbizos. | 10 acts per ward to perform at Mayoral Izimbizos function by 30 June 2016. | Target not met | 10 acts per ward to perform at Mayoral Izimbizos functions scheduled to take place by 30 September 2015. | Target not met | 10 acts performed at the Mayoral Izimbizo functions but no supporting documentation was provided to validate the achievement | 10 acts per ward to perform at Mayoral Izimbizos functions scheduled to take place by 30 September 2015. | Target not met | 10 acts performed at the Mayoral Izimbizo functions but no supporting documentation was provided to validate the achievement | 10 acts per ward to perform at Mayoral Izimbizos functions scheduled to take place by 30 September 2015. | Target not met | 10 acts performed at the Mayoral Izimbizo functions but no supporting documentation was provided to validate the achievement | 10 acts per ward to perform at Mayoral Izimbizos functions scheduled to take place by 30 September 2015. | Target not met | Not achieved | 190 acts performed at the Mayoral Izimbizo functions but no supporting documentation was provided to validate the achievement | Supporting documentation to verify that 190 acts performed at the Mayoral Izimbizo function will be filed and kept for audit trail | n/a
3.2.1 |  | to encourage self pride and curb teenage pregnancy | To educate young women on HIV and advocate for equality in women in a cultural celebration | Number of HIV meetings held. | 4 HIV meetings to be conducted by 30 June 2016. | 3 HIV meetings held on 16 September 2015, 03 November 2015 and 24 February 2016 | 1 HIV meeting to be conducted by 30 September 2015 | 1 HIV meeting conducted on 16 September 2015 | n/a | 1 HIV meeting to be conducted by 30 December 2015 | 1 HIV meeting conducted on 03 November 2015 | n/a | 1 HIV meeting to be conducted by 30 September 2015 | 1 HIV meeting conducted on 24 February 2016 | n/a | 1 HIV meeting to be conducted by 30 September 2015 | Target not met | Not achieved | A HIV meeting was held on the 4th May 2016 but no supporting documentation was provided to validate the achievement | Supporting documentation to confirm that all scheduled HIV meetings were held will be filed and kept for audit trail | Minutes and attendant register
3.3.1 |  | to prevent accidents and protect animals roaming on the roads | To ensure pound operationalisation | Number of reports on pound operation. | Quarterly reports on operation of the pound. | Target not met | Preparation of 1 report per quarter on operation of the pound by 30 September 2015 | Quarterly report on operation preparedof the pound prepared by 30 December 2015 | n/a | Preparation of 1 report per quarter on operation of the pound by 30 December 2015 | Quarterly report on operation preparedof the pound prepared by 30 December 2015 | n/a | Preparation of 1 report per quarter on operation of the pound by 30 March 2015 | Quarterly report on operation preparedof the pound prepared by 30 December 2015 | n/a | Preparation of 1 report per quarter on operation of the pound by 30 June 2015 | Quarterly report on operation preparedof the pound prepared by 30 December 2015 | Not achieved | n/a | n/a | Reports
3.4.1 |  | to encourage participation of youth in sports and recreation. | To ensure ward participation in sports and recreation. | Number of games executed. | To conduct 18 sports days with 1 sport day per ward by 30 June 2016 | Target not met | Conduction of 1 sport day per ward for 6 wards by 30 September 2015 | Target not met | 1 sport day for 6 wards was conducted but no supporting documentation was provided to validate the achievement | Conduction of 1 sport day per ward for 6 wards by 30 December 2015 | 2 sport days conducted for ward 02 & 13 on 25 November 2015 and 10 December 2015 | n/a | Conduction of 1 sport day per ward for 6 wards by 30 March 2016 | Target not met | 1 sport day for 6 wards was conducted but no supporting documentation was provided to validate the achievement | Conduction of 1 sport day per ward for 6 wards by 30 September 2015 | 2 sport days conducted for ward 05 & 19 on 06 May 2016 and 24 May 2016 | Not achieved | 18 sport days with 1 sport day per ward were conducted but no sufficient supporting documentation was provided to validate the achievement | Supporting documentation to confirm that 18 sport days were conducted will be filed and kept for audit trail | Payment vouchers and Game scores
3.5.1 |  | To empower the people of Msinga municipal area through education to increase chances of finding employment | administer busary scheme | Number of students awarded bursaries. | To award 114 students with bursaries, being 2 students per ward from the profiled most deprived households by 30 June 2016. | 114 students awarded bursaries by 30 June 2016 | To award 30 students with bursaries, being 2 students per ward from the profiled most deprived households by 30 September 2015. | 34 students awarded bursaries by 30 September 2015 | n/a | To award 28 students with bursaries, being 2 students per ward from the profiled most deprived households by 30 December 2015. | 25 students awarded bursaries by 30 September 2015 | Applications were not adequately completed | To award 28 students with bursaries, being 2 students per ward from the profiled most deprived households by 30 December 2015. | 55 students awarded bursaries by 30 March 2016 | n/a |  |  | Achieved | n/a | n/a | Bursary scheme application forms
3.5.2 |  |  | review town planning tarrifs | Reviewed town planning tarrifs. | Review town planning tarrifs by 30 June 2016. | Town planning tarrifs reviewed on 30 March 2016 | [9 empty] | Review town planning tarrifs by 30 June 2016. | Town planning tarrifs were reviewed and approved by Council on 30 March 2016 | Achieved | n/a | n/a | Council Resolution
3.5.3 |  |  | assist with the burial facilities to pauper families | Number of assisted families with burial services. | To provide burial assistance to 2 households per month per ward by 30 June 2016 | 443 households provided with burial assistance by 30 June 2016. | To provide burial assistance to 108 households with 2 households per month per ward by 30 September 2015 | 110 households provided with burial assistance by 30 September 2015 | n/a | To provide burial assistance to 108 households with 2 households per month per ward by 30 December 2015 | 111 households provided with burial assistance by 30 December 2015 | n/a | To provide burial assistance to 108 households with 2 households per month per ward by 30 March 2016 | 109 households provided with burial assistance by 30 March 2016 | n/a | To provide burial assistance to 108 households with 2 households per month per ward by 30 June 2016 | 1013 households provided with burial assistance by 30 June 2016 | Achieved | n/a | n/a | Indigent burial register.
3.5.4 |  |  | Community works programme /EPWP | Number of CWP projects implemented. | 19 CWP projects implemented with 1 project per ward. | Target not met | Implementation of 19 CWP projects with 1 project per ward. | Target not met | 19 CWP projects implemented but no supporting documentation was provided to validate the achievement | Implementation of 19 CWP projects with 1 project per ward. | Target not met | 19 CWP projects implemented but no supporting documentation was provided to validate the achievement | Implementation of 19 CWP projects with 1 project per ward. | Target not met | 19 CWP projects implemented but no supporting documentation was provided to validate the achievement | Implementation of 19 CWP projects with 1 project per ward. | Target not met | Not achieved | 19 CWP projects implemented but no supporting documentation was provided to validate the achievement | n/a | Monthly CWP reports.
3.5.5 |  |  | attend to disability issues | Number of disability forums held. | To attend disability issues on occurance. | 2 disability forums attended: 18 August 2015 and 06 November 2015. | No quaterly target ( issues are attended as they occur) | 1 disability forum meeting sat on 18 August 2015 | n/a | No quaterly target ( issues are attended as they occur) | 1 disability forum meeting sat on 06 November 2015 | n/a | [5 empty] | Achieved | n/a | n/a | Minutes
4.1.1 | MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | to improve financial viability in the municipality | to promote sound financial practices in the municipality through sound policies. | Proof of submission to AG. | Submission of AFS to AG by 31 August 2015. | The AFS were submitted to the AG on 29 August 2015. | Submit AFS to AG by 31 August 2015 | AFS were submitted to AG on 28 August 2015 | n/a | [8 empty] | Achieved | n/a | n/a | Acknowledgement letter from the AG.
4.1.2 |  |  |  | Approved three year budget . | Approval of three year budget by Council by 30 June 2016. | Three year budget approved by Council on 25 May 2016. | [9 empty] | Approval of three adjusted budget by 30 June 2016 | Budget approved by Council | Achieved | n/a | n/a | Council resolution
4.1.3 |  |  |  | Clean audit opinion by the AG. | To obtain a clean audit from the AG for the 2014/2015 financial. | The municipality obtained a clean audit for the 2014/2015 financial year |  |  |  | To obtain clean audit from AG | Clean audit was obtained from AG | n/a | [5 empty] | Achieved | n/a | n/a | Audit report from the AG.
4.2.1 |  |  | To monitor credit control | Number of s71 reports submitted to National and Provincial Treasuries. | To submit 3 section 71 reports per quarter to the National and Provincial Treasury by 30 June 2016. | Monthly section 71 reports submitted to the NT & PT. | Section 71 Monthly reports | Section 71 Monthly reports submitted to National and Provincial Treasury | N/A | Section 71 Monthly reports | Section 71 Monthly reports submitted to National and Provincial Treasury | n/a | Section 71 Monthly reports | Section 71 Monthly reports submitted to National and Provincial Treasury | N/A | Section 71 Monthly reports | Section 71 Monthly reports submitted to National and Provincial Treasury | Achieved | n/a | n/a | Email of acknowledgement from NT &PT
5.1.1 | CROSS CUTTING INTERVENTIONS | to accelerate the town establishment and ensure spatial representation of the IDP | ensure proper spatial & environmanetal planning | Town establishment. | To facilitate formalisation of town and proclamation of Tugela Ferry as a town by 30 June 2016. | Target not met | [11 empty] | Not achieved | The project was called off due to disagreements between two tribes who own the land. | Land stakeholders have been contacted for intervention. | n/a
5.1.2 |  |  | to speed up development applications in terms of KZN PDA | Number of development applications processed. | 4 quarterly development applications processed by 30 June 2016. | Target not met | 1 quarterly development application processed by 30 September 2015. | Target not met | New legislation came in and there were delays, had to put structures in place for the new legislation | 1 quarterly development application processed by 30 December 2015. | Target not met | New legislation came in and there were delays, had to put structures in place for the new legislation | 1 quarterly development application processed by 30 March 2016. | Target not met | New legislation came in and there were delays, had to put structures in place for the new legislation | 1 quarterly development application processed by 30 June 2016 | Target not met | Not achieved | New legislation came in and there were delays, had to put structures in place for the new legislation | Structures to be inserted to align with the new legislation. | n/a
5.2.1 |  | to create a disaster free enviornment | Adopt Disaster management Plan | Approved Disaster Management plan. | Adoption of Disaster Management Plan by 30 June 2016. | Disaster Management Plan approved on 09 December 2015. |  |  |  | Adoption of Disaster management plan | Disaster management plan was adopted by Council on 09 December 2015 | n/a | [5 empty] | Achieved | n/a | n/a | Council Resolution
5.2.2 |  |  | 12 Awareness programmes | Number of awareneses conducted. | Conduction of 12 Disaster awareness programs in Msinga area by 30 June 2016. | Only 5 awarenesses were conducted: Douglas Clinic- 2 August 2015; Rorkes Drift Clinic- 19 August 2015; Elandskraal Clinic- 19 August 2015; Pomeroy health centre- 25 August 2015; and Siyabonga school- 19 April 2016. | Conduction of 3 Disaster awareness programs in Msinga area by 30 September 2015 | 4 awarenesses were conducted: Douglas Clinic- 2 August 2015; Rorkes Drift Clinic- 19 August 2015; Elandskraal Clinic- 19 August 2015; and Pomeroy health centre- 25 August 2015 | n/a | Conduction of 3 Disaster awareness programs in Msinga area by 30 December 2015 | Target not met | Lack of capacity | Conduction of 3 Disaster awareness programs in Msinga area by 30 March 2016 | Target not met | Lack of capacity | Conduction of 3 Disaster awareness programs in Msinga area by 30 March 2016 | Siyabonga school- 19 April 2016. | Not achieved | Lack of adequate capacity | The municipality will allocate more personnels to conduct awareness programs in the 2016/2017 financial year | Awareness checklists
5.3.1 |  |  | Management of disasters | Number of incidents reported. | 4 quarterly disaster management reports to be prepared by 30 June 2016. | 4 quarterly disaster management reports were prepared by 30 June 2016. | Preparation of quarterly disaster management reports | Disaster management quarterly report prepared | n/a | Preparation of quarterly disaster management reports | Disaster management quarterly report prepared | n/a | Preparation of quarterly disaster management reports | Disaster management quarterly report prepared | n/a | Preparation of quarterly disaster management reports | Disaster management quarterly report prepared | Achieved | n/a | n/a | Quarterly reports
6.1.1 | GOOD GOVERNANCE AND PUBLIC PARTICIPATION | To improve the perfomance of the muniipality inorder to ensure sustainability. | IA to report on PMS | Number of IA reports submitted to Audit Committee. | Tabling of quartely audit reports to audit committee. | 4 quarterly Internal Audit reports were tabled to the Audit Committee | 1 IA report tabled to AC per quarter | IA report table dto AC | n/a | 1 IA report tabled to AC per quarter | IA report table dto AC | n/a | 1 IA report tabled to AC per quarter | IA report table dto AC | n/a | 1 IA report tabled to AC per quarter | IA report table dto AC | Achieved | n/a | n/a | Internal Audit reports
6.1.2 |  |  | Perfomance agreements signed in line with IDP | Number of signed performance agreements. | Senior Managers' signing of performance agreements by 30 June 2016. | Performance evaluations were conducted for the Director Technical Services, Director Development and Planning Services, Municipal Manager and IDP manager by 31 July 2015. | Senior Managers' signing of performance agreements by 30 June 2016. | Performance evaluations were conducted for the Director Technical Services, Director Development and Planning Services, Municipal Manager and IDP manager by 31 July 2015. | The Director Corporate and Community Services is Acting, therefore, no performance evaluation was constructed. The CFO is consulting, therefore, evaluations were not done. | [8 empty] | Not achieved | The Director Corporate and Community Services is Acting, therefore, no performance evaluation was consucted. The CFO is consulting, therefore, evaluations were not done. | The DCCS will be recruited in the 2016/2017 financial year. | Performance file
6.2.1 |  | fill strategic vacancies | Fill the number of vacancies on the approved Organogram. | Number of vacancies filled. | 9 vacancies to be filled by 30 June 2016. | 9 vacancies were filled: Demand and acquisition management officer, Stores management officer, Cybercadet, Municipal Manager's driver, Building inspector, Fire fighter (x3) and Internal Auditor vacancies filled by 30 June 2016. | 3 vacancies filled by September 2015 | 2 people were appointed by September 2016 | Threre were delays in the recruitment and the Municipality obted to make appointments on the next quarter. | 3 vacancies filled by 31 December 2015 | 6 vacancies were filled by 31 December 2015 | n/a | 3 vacancies filled by 30 March 2016 | 2 vacancies were filled by 30 March 2016 | Target was met |  |  | Achieved | The Director of Corporate and Community Services post is vacant as the municipality was waiting for elections before hiring. | DCCS to be appointed by 28 February 2017. | Internal Advertisments and appointment letters
6.3.1 |  | to ensure public participation in local governance | ensure effective functioning of council structures | Number of meetings held. | 38 izimbizo by 30 June 2016. | 38 Izimbizo events took place in the financial year. | 7 izimbizo events held by 30 September 2014 | 7 izimbizo events were held by 30 September 2015 | N/A | 10 izimbizo events held by 30 December 2015 | 10 izimbizo events were held by 30 December 2015 | N/A | 12 izimbizo held by 30 March 2016 | 10 izimbizo events were held by 30 March 2016 | N/A |  |  | Achieved | n/a | n/a | List of Mayoral programmes
6.3.2 |  |  |  | Number of mayoral talk shows. | 12 radio shows by 30 June 2016. | 12 radio shows were conducted on 10 August 2015, 14 September 2015, 12 October 2015, 09 November 2015, 14 December 2015, 11 January 2016, 08 February 2016, 14 March 2016, 11 April 2016, 09 May 2016, 13 June 2016 and 11 July 2016. | 3 Mayoral radio shows to be held by 30 September 2015 | Radio shows were conducted on the following dates: 10 August 2015and 14 September 2015 | The next scheduled show is in the 2nd quarter | 3 Mayoral radio shows to be held by 30 December 2015 | Radio shows were conducted on the following dates: 12 October, 09 November 2015 and 14 December 2015 | n/a | 3 Mayoral radio shows to be held by 30 March | Radio shows were conducted on the following dates: 11 January 2016, 08 February 2016 and 14 March 2016 | n/a | 3 Mayoral radio shows to be held by 30 June 2016 | Radio shows were conducted on the following dates: 11 April 2016, 09 May 2016 and 13 June 2016 | Not achieved | All scheduled 2015/2016 shows were executed | n/a | List of Mayoral talkshows from Khwezi Radio.
6.4.1 |  | To conduct trainings for ( staff/councillors/ward commitees). | To implement WSP. | Number of trainings held. | Training of Councillors with 1 Councillor per ward by 30 June 2016. | Target not met |  |  |  | Training of 17 councillors by 30 December 2015 | Target not met | Training of Councillors was conducted but no sufficient supporting documentation was provided to validate the achievement | [5 empty] | Not achieved | Training of Councillors was conducted but no sufficient supporting documentation was provided to validate the achievement | Supporting documentation to confirm that Councillors were trained will be filed and kept for audit trail | List of Councillors attended training.
LEGENDS:
Target met in previous quarters
No target due for the quarter
Information not provided or insufficient
No target for the financial year